## Slide 1: MS Project
November 2025

## Slide 2: Day 1
Introduction
Step-by-step plan
Settings
Task 1
Project information
Task 2
Calendars
Work Breakdown Structure
Guided tour
Tasks
Task 3
Plans, tasks & Reports
  Create project plan
  Inserts Tasks & Dependencies
  Add Resources & Allocate
  Reports
  Analyzes
  Adapt a project
Link to files

## Slide 3: Become acquainted
Company
Nature of the work (in relation to projects)
Experiences (Office / MS-project)
What is your objective?
What do you want to learn?
Notes: Voornaam
Achternaam
E-mailadres
Anita
Drost
a.drost@enschede.nl
Berdien
Knottenbelt
b.knottenbelt@enschede.nl
Kenneth
Bunskoek
kenneth.bunskoek@tecnotion.com

## Slide 4: Why MS Project
Can be more productive and get better results by using the set of features that Project provides. You can use Project to:
Create plans at the level of detail that's right for your project. Working with summary data initially and then switch to a more granular approach if necessary. Tasks can be scheduled automatically, and which tasks you want to schedule Manual scheduling. Manage tasks, resources, work, and costs at any level of detail Work with your plan's data in a variety of views and reports. Track and manage your plan throughout the project's lifespan. Collaborate and share data with others in your organization. Use resource pools, consolidated projects, and links between projects to optimize your Focus on project management across multiple projects

## Slide 5: Step-by-step plan
Initiation
Baseline plan
Management of the project

## Slide 6: Steps
 | Step | 
1 | Definition | Start date, PM, acceptance criteria
2 | Calendar | Bank holiday, vacations
3 | Work Break Down | Structure based on tasks, or products, how detailed
4 | Dependencies | Fase’s, logical sequence, lags
5 | Constrains | Deadlines, other projects
6 | Resources | Men, machines, materials
7 | Assignments | Resources assign to tasks, availability resources
8 | Check allocations | Over allocation, lags between work
9 | Progress | Now the work starts: monitor every week the progress and adjust the plan
10 | Re-plan | Milestones, resources, tasks, changes
12 | Report | Management information, progress reports

## Slide 7: MS-project
Basis
  Project
  Task
  Resource
work
duration
Percentage
available

## Slide 8: Start a project

## Slide 9: Start a project
Escape <Esc>
Blank project

## Slide 10: Start a project

## Slide 11: Settings

## Slide 12: Euro settings & Entry bar
File
Options

## Slide 13: Schedule
Recommendation
Autolink: disabled
Notes: Neem alle opties mee

## Slide 14: Autosave
Recommendation
Auto save: disabled

## Slide 15: Advanced
Recommendation
Automatically add resource: disabled
Prompt for project info for … :enabled
Show summery tasks: enabled
Move end of completed part: enabled
- And move start.. : ?
Move start of remaining part: enabled
- And move start.. : disabled

## Slide 16: Settings everyone
Default view: Gantt with Timeline
Date format: day & date
Symbol: €
Entry bar
New tasks created : Manually scheduled
Auto scheduled: Project Start date
Default task type: fixed Unites
New Tasks are effort driven

## Slide 17: Practical task 1
CH02 Practical Task 1

## Slide 18: Resource View & Calendar
WBS example.mpp (MS-project)

## Slide 19: CH02 Practical TASK 1
TakeGuidedTour.MPP
Resources
Reports
  Dashboard
  Resources
    Resource Overview
Link to files

## Slide 20: Practical files
https://1drv.ms/f/c/cedf024df8b0d021/Eg4kpRgsPilIuYJnH2r034IB99xR7-TZHsBT46x5q2VQzw?e=byELB8

## Slide 22: Most important of the office ribbon
End chapter

## Slide 23: Project information
In het lint
Info in het bestand

## Slide 24: Project information (1)

## Slide 25: Project information (2)
Don’t update this, all calculated values will be updated!

## Slide 26: Project information (3)

## Slide 27: CH03 Practical TASK 2
New plan
Start date 18-01-2018
Nonworking day 18-01-2018
Properties project
Subject: New book launch schedule
Manager: Carole Poland
Company: Lucerne Publishing
Comments: New children’s book for spring release
End chapter

## Slide 28: Calenders
Project
Resource
Task

## Slide 29: Project calendar

## Slide 30: Change a day

## Slide 31: Make a weekend a working day
Use “Del” to delete 13:00 – 17:00
(Mac fn – Backwards)

## Slide 32: Feestdagen Nederland
Nieuwjaarsdag: donderdag 1 januari
Goede Vrijdag: vrijdag 3 april
Eerste Paasdag: zondag 5 april
Tweede Paasdag: maandag 6 april
Koningsdag: maandag 27 april
Bevrijdingsdag: dinsdag 5 mei
Hemelvaartsdag: donderdag 14 mei
Eerste Pinksterdag: zondag 24 mei
Tweede Pinksterdag: maandag 25 mei
Eerste Kerstdag: vrijdag 25 december
Tweede Kerstdag: zaterdag 26 december

## Slide 33: New calendar – Denmark (2026)
Notes: Nieuwjaarsdag: 1 januari
Palmpasen: 29 maart
Pasen: 3 april
2e Paasdag: 6 april
Grote Vrijdag: 10 april
Gebedspost: 8 mei
Hemelvaartsdag: 14 mei
Pinksteren: 24 mei
2e Pinksterdag: 25 mei
Dag van de Grondwet: 5 juni
Midzomer: 24 juni
Kerstmis: 25 december
2e Kerstdag: 26 december

## Slide 34: Work Break Down Structure (WBS)

## Slide 35: Demo: taken invoeren
3 teken en dan een samenvattende taak
Eerst fasen en dan de onderliggende taken

## Slide 36: Create task or milestone
Insert button

## Slide 37: Fill in task duration or dates
Insert knop

## Slide 38: Top-down of bottom-up
Top-down
  Start with different phases First summary task and then detail tasks
Bottom-up
  First the details Then summarize End determined

## Slide 39: Create summary tasks to outline the plan
Indent increase or decrease Click multiple task and create summarizations

## Slide 40: Opdracht: taken invoeren
Instelling: handmatige scheduled –Projectnaam: De grote verbouwing
Voorbereiding
  Maken bouwplannen
  Aanvragen vergunning
  Contracteren aannemer
Uitvoering
  Slopen en bouwen
  Installeren keuken
  Afwerken geheel
Afronding
  Goedkeuring bouwinstantie
  Feestje

## Slide 41: Demo: mijlpalen
Mijlpaal direct invoeren
Taak via duration = 0 maken
Taak details gebruiken

## Slide 42: Bestanden van de syllabus
https://1drv.ms/f/c/cedf024df8b0d021/EojbofAxZz9Eu_9TLOPFAeUBrhUMItHKRHxK6ap_RWnLgg?e=w6r4LC

## Slide 43: Opdracht: Mijlpalen invoeren
Gebruik : Project2025-3.mpp
Voorbereiding
  vergunning verleend
  Voorbereiding gereed
Uitvoering
  Start bouw
  Goedkeuring fundering
  Uitvoering klaar
Afronding
Einde projectverbouwing

## Slide 44: Use of outline

## Slide 45: Opdracht: Outline
Gebruik : Project2025-4.mpp

## Slide 46: Opdracht: Maak alle taken automatisch
Gebruik : Project2025-4.mpp

## Slide 47: Afhankelijkheden

## Slide 48: Opdracht: afhankelijk
Gebruik : Project2025-5.mpp
De voorbereiding moet in zijn geheel zijn afgerond voordat de uitvoering kan beginnen
Pas als de architect is gevonden (en aangenomen) kan begonnen worden met het uitwerken van het ontwerp (de bouwtekeningen)
Zodra de bouwtekeningen gereed zijn kan de vergunning worden aangevraagd. Uiteraard kan pas daarna de vergunning verleend worden
Pas als de vergunning definitief is zal de aannemer worden gecontracteerd.
Nadat de aannemer is gecontracteerd zijn we klaar met de voorbereiding.
Zodra de bouw van start kan, kunnen gelijktijdig de sloop van de buitenmuur en de sloop van de keuken beginnen. Om zeker te zijn dat zulks ook gebeurt moet de afhankelijkheid in de planning worden opgenomen.
Zodra de buitenmuur gesloopt is kan worden begonnen met het storten van de nieuwe fundering. Zodra dat achter de rug is kan de fundering worden gekeurd.
De bouw van de uitbouw is afhankelijk van zowel de nieuwe fundering als de sloop van de oude keuken
Als de uitbouw af is kan worden begonnen met zowel het plaatsen van de keuken als het afwerken.
Als de keuken af is en het afwerken (ook aan de binnenzijde), is de uitvoering klaar.
De goedkeuring door de bouwinstanties gaat alleen over de fundering en de structurele kwaliteit van de uitbouw. De keuken zelf heeft daar geen invloed op. Zodra de uitbouw af is kan de inspectie plaatsvinden.
Als de uitbouw is goedgekeurd én de uitvoering is geheel af, dan is het tijd voor een feestje om de nieuwe keuken in te wijden.
Na het feest kan het project worden afgesloten..

## Slide 49: Guided Tour MS-project
Quick Access - Ribbon – Tabs
Screen tips
Right Mouse button
  Task
  Bar
Templates
  Set once, use many times
  Examples
Table view
Gantt Chart

## Slide 50: Explore the Project user interface – Task / Resource
Task, Resource, Project
Views -> Gant-chart – Resource – Task
Schedule -> 0 until 100% or “Update”
Assign Resources
Resource pool
Level

## Slide 51: Explore the Project user interface – Project / View - Table
Baseline
Update project
Subprojects
Tables
Time scale
Timeline

## Slide 52: Resource sheet

## Slide 53: Resource usage

## Slide 54: Reports

## Slide 55: Timeline

## Slide 57: Task - topics
Create task Adjust task duration & dates Milestones Summary tasks Dependency between tasks Task Manual to Automatic Check plan duration and end date

## Slide 58: Making tasks dependent
Drag and drop
Task details
Gantt - table
Ctrl – select
Menu

## Slide 59: Link tasks

## Slide 60: Taken Modes

## Slide 61: Task all fields (information)
Add a note
Add a hyperlink (right click)

## Slide 62: Project summary task

## Slide 63: Task options

## Slide 64: Task type
Fixed units, effort driven (initially)
Fixed duration, more resources, more hours
Fixed work, more resources, shorter duration
Fixed units, percentage per resource fixed

## Slide 65: Chat GPT
In Microsoft Project, a Task Type defines how the software calculates changes to tasks when you modify one of the three key variables:
Work (the total effort required to complete the task)
Duration (the amount of time the task will take)
Units (the number of resources assigned, often shown as a percentage)
MS Project uses these relationships:
Work = Duration × Units

## Slide 66: Task type fixed Units
Fixed Units
Default setting in MS Project
Units (resources assigned) stay constant.
If you change the duration, MS Project recalculates work.
If you change work, it recalculates duration.
Example:
If a task has 2 resources (200% units) and takes 2 days (duration), the total work is 2 resources × 2 days = 4 days of work.
If you increase the duration to 4 days, MS Project keeps 2 resources and updates the work to 8 days.

## Slide 67: Task type fixed Work
Fixed Work
Work stays constant.
Changing duration will change units.
Changing units will change duration.
Best when: You know exactly how much effort is needed (e.g., 16 hours of work), regardless of how long it takes or how many resources are assigned.

## Slide 68: Task type fixed Duration
Fixed Duration
Duration stays constant.
Changing units will change work.
Changing work will change units.
Best when: The task must be completed in a specific time frame, no matter how many resources are available.

## Slide 69: Task type – what happen
Task Type | What stays fixed | What changes when you edit duration | What changes when you edit work | What changes when you edit units
Fixed Units | Units | Work | Duration | Work
Fixed Work | Work | Units | Duration | Duration
Fixed Duration | Duration | Work | Units | Work

## Slide 70: Task – effort driven
The effort driven field indicates whether the scheduling for a task is effort driven.
The total task work stays the same regardless how many resources are assigned.
The remaining work is distributed to them.

## Slide 71: Resources
Resource Sheet
  New
  Insert
  Delete
Maximum capacity
  100% per person
  X00% for a group of x resources
Rates
  Normal
  Overrate
Costs of item
Adjust the calendar, or
one calendar per person/group
Adjust working hours

## Slide 72: Resources
Resource Sheet
  Work
  Cost
  Material
Financials
  Total

## Slide 73: CH05 Practical TASK 4
The SimpleSetUpResources practice file for these tasks is located in the
Project2016SBS\Ch05 folder
  Create resources
  Maximum capacity
  Rates & costs
  Working time per resource
  Add a note

## Slide 74: What we learned about resources
Create a resource Maximum capacity Rates Working hours Cost resource Resource Note
End chapter

## Slide 75: Day 1 – looking back
What did you learn? What do you still have trouble with? What went well? What could be better? What do you want to practice next week? What do you want to learn next week?